## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Gabriel | 6800 | 5400 | 1400 | 5100 | 4450 | 650 | 1000 | 350 | 650 | 700 | 600 | 100
Kyle | 4050 | 5525 | -1475 | 2350 | 4300 | -1950 | 1000 | 425 | 575 | 700 | 800 | -100
Michael | 8700 | 12225 | -3525 | 3500 | 5600 | -2100 | 1000 | 425 | 575 | 4200 | 6200 | -2000
Oshan | 3900 | 1600 | 2300 | 2700 | 1200 | 1500 | 1000 | 350 | 650 | 200 | 50 | 150
Robert | 3600 | 2600 | 1000 | 2400 | 2300 | 100 | 1000 | 250 | 750 | 200 | 50 | 150
Zach | 4200 | 3850 | 350 | 2500 | 3050 | -550 | 1000 | 250 | 750 | 700 | 550 | 150
Total | 31250 | 31200 | 50 | 18550 | 20900 | -2350 | 6000 | 2050 | 3950 | 6700 | 8250 | -1550

## Gantt
| predicted time(hrs) | time spent(hrs) | key |  | completed |  | this week |  | planned
Gabriel |  |  | hours | 0 |  | 1 | 2 | 3 |  | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
UI Text and Graphic Design | 8 | 3
Start Menu | 6 | 3.5
Inventory System (Programming/ Graphics) | 10 | 4
Properly Communicating Back and Forth With item System (Programming) | 10 | 1
Heads Up Display (Programming / Graphics) | 8 | 4
Properly Communicating Back and Forth with Character Stats (Programming) | 4 | 4
Blender Modeling | 0 | 6
Testing | 5 | 5
Learning Unity System | 0 | 14
Total> | 51 | 44.5
Kyle | 0 | 0
Learning Unity System | 0 | 10
Implementing Item Database | 2 | 2
Adding Items/Powerups | 10 | 22
Gaant Chart Management | 3 | 2.5
Documentation | 2 | 0
Testing | 6 | 0
Added Powerups to Item Database | 0.5 | 0.5
Singleton/Decorator Patterns | 4 | 6
Total> | 23.5 | 43
Michael
Collect Requirements | 6 | 4
Layout Design | 6 | 8
Generation Algorithm | 6 | 9
Implementation/Programming | 8 | 23
Documentation | 6 | 6
Testing | 3 | 6
Total> | 35 | 56
Oshan | 0 | 0
Collect Requirements | 4 | 4
Designing Characters/ Collect Prefabs | 8 | 5
Movement Behavior | 3 | 3
Auxilary Functions | 6 | 0
Testing and laser attack | 6 | 0
Patterns and Attack hits | 0 | 0
Total> | 27 | 12
Robert | 0 | 0
Identify Requirements | 1 | 3
Design system | 5 | 20
Program system | 6 | 0
Documentation | 3 | 0
Testing | 3 | 0
Changes after testing | 3 | 0
Final Testing | 3 | 0
Total> | 24 | 23
Zach | 1 | 1
Identify Requirements | 1 | 1
Design System | 5 | 3
Program Basic System | 5 | 6
Documentation | 1 | 2
Integrate Level Layouts | 5 | 5
Integration Testing | 2 | 2
Build Advanced System | 5 | 6
Final Testing | 1 | 5.5
Total> | 25 | 30.5

## Meetings
| Date |  |  |  |  | 2019-03-22
| Purpose | First Meeting | Ananlysis Planning | RFP Meeting | Presentation | Test Cases
| Hours | 1 | 1 | 0.5 | 0.75 | 1
Gabriel | 3.5 | ü | ü | ü |  | ü
Kyle | 4.25 | ü | ü | ü | ü | ü
Michael | 4.25 | ü | ü | ü | ü | ü
Oshan | 3.5 | ü | ü | ü |  | ü
Robert | 2.5 | ü | ü | ü
Zack | 2.5 | ü | ü | ü
Total | 20.5 | 6 | 6 | 3 | 1.5 | 4 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Gabriel | Individual schedule | 0 | 0
| Champion | 5 | 5
| RFP (3 , 4) | 2 | 1 | bar: 6
| Subtotal | 7 | 6
Kyle | Individual schedule | 0 | 0
| Champion | 5 | 6
| RFP (7,8,9,10) | 2 | 2 | bar: 6
| Subtotal | 7 | 8
Michael | Individual schedule | 35 | 56
| Champion | 5 | 5
| RFP | 2 | 1 | bar: 7
|  | 0 | 0
|  | 0 | 0
| Subtotal | 42 | 62
Oshan | Individual schedule | 0 | 0
| Champion | 5 | 5
| RFP (5,6) | 2 | 0.5 | bar: 6
| Subtotal | 7 | 5.5
Robert | Individual schedule | 0 | 0
| Champion | 5 | 5
0
| Subtotal | 5 | 5
Zach | Individual schedule | 0 | 0
| Champion | 5 | 5
| RFP (1,2) | 2 | 1
| Subtotal | 7 | 6
| Total | 75 | 92.5
red is dependent on others