## Management Summary
| Total |  |  | Coding |  |  | Meetings |  |  | Systems Analysis
| Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit | Budgeted | Actual | Deficit
Gabriel | 700 | 600 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 600 | 100
Kyle | 700 | 800 | -100 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 800 | -100
Michael | 700 | 600 | 100 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 600 | 100
Oshan | 200 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 50 | 150
Robert | 200 | 50 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 200 | 50 | 150
Zach | 700 | 550 | 150 | 0 | 0 | 0 | 0 | 0 | 0 | 700 | 550 | 150
Total | 3200 | 2650 | 550 | 0 | 0 | 0 | 0 | 0 | 0 | 3200 | 2650 | 550

## Gantt
Master Gaant Chart w/ 30 Minute Time Intervals | Color Key | Completed | In Progress |  | Planned
Name and Todo Item | Predicted Time Needed in Hours | Actual Time Needed in Hours | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51
Gabriel
TBD | 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
Kyle
TBD | 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
| 0 | 0
Michael
Collect Requirements | 6 | 4
Layout Design | 6 | 8
Generation Algorithm | 6 | 9
Implementation/Programming | 8 | 12
Documentation | 6 | 0
Testing | 3 | 0
Oshan
Collect Requirements | 4 | 4
Designing Characters/ Collect Prefabs | 8 | 5
Movement Behavior | 3 | 3
Auxilary Functions | 6 | 0
Testing | 6 | 0
| 0 | 0
| 0 | 0
Robert
Identify Requirements | 1 | 3
Design system | 5 | 20
Program system | 6 | 0
Documentation | 3 | 0
Testing | 3 | 0
Changes after testing | 3 | 0
Final Testing | 3 | 0
Zach
Identify Requirements | 1 | 1
Design System | 5 | 3
Program Basic System | 5 | 6
Documentation | 1 | 2
Integrate Level Layouts | 5 | 5
Integration Testing | 2 | 2
Build Advanced System | 5 | 6
Final Testing | 1 | 4.5
group totals ($) | 11100 | 9750

## Meetings
| Date | 2019-01-24 | 2019-01-26
| Purpose | First Meeting | Ananlysis Planning | Gannt Chart | Presentation | Initial Set-up | Initial Set-up | Initial Set-up | Initial Release | Team Lead 2 demo practice | Test Code Integrateion
| Hours | 1 | 1 | 0.5 | 2
Anne | 4.5 | ü | ü | ü | ü
Bill | 4.5 | ü | ü | ü | ü
Chris | 4.5 | ü | ü | ü | ü
Dan | 4.5 | ü | ü | ü | ü
Dan | 4.5 | ü | ü | ü | ü
Dan | 4.5 | ü | ü | ü | ü
Total | 27 | 6 | 6 | 3 | 12 | 0 | 0 | 0 | 0 | 0 | 0
ü

## SA
| Task | Predicted(hrs) | spent(hrs) | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15
Gabriel | Individual schedule | 0 | 0
| Champion | 5 | 5
| RFP (3 , 4) | 2 | 1 | bar: 6
| Subtotal | 7 | 6
Kyle | Individual schedule | 0 | 0
| Champion | 5 | 6
| RFP (7,8,9,10) | 2 | 2 | bar: 6
| Subtotal | 7 | 8
Michael | Individual schedule | 0 | 0
| Champion | 5 | 5
| RFP | 2 | 1 | bar: 7
|  | 0 | 0
|  | 0 | 0
| Subtotal | 7 | 6
Oshan | Individual schedule | 0 | 0
| Champion | 5 | 5
| RFP (5,6) | 2 | 0.5 | bar: 6
| Subtotal | 7 | 5.5
Robert | Individual schedule | 0 | 0
| Champion | 5 | 5
0
| Subtotal | 5 | 5
Zach | Individual schedule | 0 | 0
| Champion | 5 | 5
| RFP (1,2) | 2 | 1
| Subtotal | 7 | 6
| Total | 40 | 36.5
red is dependent on others